## Project workplan
Outputs | Activities |  | Yr 1 |  |  |  | Yr 2 |  |  |  |  | Yr 3 |  |  |  |  | Yr 4
|  |  | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4
Outcome 1. Strategic Policy & Planning
1.1: Transboundary Diagnostic Analysis of threats to the Baikal Basin ecosystem including Hövsgöl lake in Mongolia completed | 1a) Establish Science Advisory Group
1b) Hold Science Symposium within 6 months of project inception
1c) Hold stakeholder meetings, to include civil society, industry and local government representatives, to discuss ecosystem threats.
1d) Revise and enhance preliminary TDA, including causal chain analysis
1e) Update TDA as a Baikal Basin State of the Environment Report no later than 6 months prior to the end of the project, including evidence of status changes since the initial TDA.
1.2: Study on Selenga Delta habitat and water quality issues, including PTS and nutrient loading, water level fluxes and health of sediment and benthic organisms | 2a) Establish / upgrade monitoring sites at inflow, midpoint and outflow locations in the Delta.
2b) Establish baselines relating to water balance and fluxes, water quality, the composition of benthic systems and sediment, diversity of aquatic flora and fauna (including presence of alien species), and presence/use of terrestrial species.(yr 1-2)
2c) Develop and present analysis on the impact to delta flora and fauna of changing water conditions, including recommendations on optimal flows; as well as in-stream constructed wetlands and other design options to reduce the flow of pollutants into and through the delta (yr 2)
2d) Monitor water quality and flora/fauna conditions at monitoring sites on permanent basis
1.3Assessment of transboundary problems in integrated surface and ground water resources management in the Baikal Basin and corresponding pollution threats. | 4a) Undertake groundwater assessment of the basin using available monitoring sites.
4b) Provide monitoring results for the Basin Database, TDA and SOE reports.
4c) Link with training / capacity building activities (see output 2.1.4) to improve environmental inspections and enforcement of regulations for avoiding groundwater contamination.
4d) Develop and cost out recommended national groundwater management policies for each country, including inter-sectoral integration and planning, well head protection, expanded groundwater monitoring (see output 2.1.5)
1.4 Pollution hot spot assessment of the Basin, including a prioritized list of projects to be considered for future investment, the development of prefeasibility studies and revised regulations to reduce industrial pollution loading into the Baikal/Selenga basin. | 5a) Identify and map all significant industrial hot spots in the Basin, including both active and closed industrial facilities. Prioritize hot spot list based on significance of known risk to surface and groundwater, focusing on: a) waters used for drinking water abstraction, b) proximity to PA, Lake Baikal and Lake Hövsgöl, and spawning grounds c) specific hazardous pollutants used in processes or stored d) significant threat in case of natural disaster: e.g. earthquake or flood.
5b) Review and rank upgrade needs for Selenga basin municipalities, including ID of ongoing and planned water and sanitation projects.
5c) Provide assistance to high risk / high priority hot spots for a) development of pre-feasibility studies for remediation on closed facilities, b) training for active concerns on PTS, POPs & UPOPs, management, c) recommendations on environmental investments on active concerns to reduce pollution discharge.
5d)Develop recommendations on revised regulations and inspection policies for large industrial facilities in the region
1.5. Strategic Action Programme (SAP) under implementation, including joint actions to enhance ecosystem protection | 6a) Form ad hoc SAP drafting group to develop and submit draft SAP for consideration by the Science Advisory Group and Joint Commission.
6b) Submit SAP draft to both governments for approval at Ministers meeting (Yr 3)
6c) Provide advise and assistance to both countries on SAP implementation (yr 4)
6d) Monitor country achievement of SAP implementation
1.6: Biodiversity conservation standards for tourism, mining, fisheries and livestock management developed, integrated in SAP and local legislation, regional development plans; with amendments to EIA policies to address biodiversity risks; | 7a) Elaborate best practice conservation standards for tourism, mining using international and regional examples.
7b) Provide gap analysis concerning best practices and the existing policies and standards in Russia and Mongolia. Develop recommendations for changes to local and national policies, legislation and regional development plans to enhance biodiversity protection.(Build on findings and recommendations from self-assessments developed in 2.1.3)
7c) Propose ecotourism and pollution avoidance aspects for tourism plans in the region, especially those being developed in Irkutsk and Buryatia.
1.7: Sub-basis watershed management plans development (for Mongolia) and implemented (for Russia). | 8ma) hold kick off meeting with local officials in each basin
8mb) collect data on economic activities, such as transportation, industry, agriculture and tourism and their impacts on the environment: (e.g. water quality, biodiversity),
8mc)draft sub-basin management plan(s)
8md) present plan(s) to key stakeholders in series of workshops
8me) revise and submit plans for government approvals
8mf) establish training and capacity building as necessary for newly responsible agencies
8mg) assist Mongolian government on policy and legal changes requires
8mh) Hold workshops with agencies focusing on industrial development and tourism to forge cooperation
In Russia:
8ra) Assess current basin management strengths and weaknesses
8rb)Launch capacity building and training program (also see output 2.1.4.)for sub basin managers, on integrated planning, mapping using GIS, and biodiversity monitoring
8rc) Hold workshops with agencies focusing on industrial development, transportation and tourism to forge closer cooperation.
Outcome 2: Institutional strengthening for Integrated Water Resource Management (IWRM)
2.1: Joint Commission for the Baikal / Selenga Basin established and capacitated on the basis of the current joint Russian - Mongolian Task Force on Transboundary Water Use and Protection. | 1a) Assist countries with selection, capacity building and information transfer to new Joint Commission participants
1b) Facilitate Joint Commission inception meeting and annual meetings
1c) Facilitate support of Science Advisory Group to the Joint Commission
1d) Support Joint Commission review process for TDA and SAP approvals
1e) Support Joint Commission efforts to draft new Treaty
2.2:Inter-ministerial committees at national levels tasked with managing the decision-making process to approve and implement Baikal basin initiatives, incl. integrated sub-basin watershed management plans, TDA/SAP. | 2a) Designation by countries of participants and holding of interministerial meetings
2b) At country request, participate in interministerial meetings to clarify purpose, benefits and impacts of proposals, including TDA/SAP, transboundary waters treaty, etc.
3a) Develop guidance for self-assessments
3b) Hold training workshops for persons carrying out self-assessments
2.3:Training program carried out for key actors in an improved and enhanced, long-term transboundary management of Baikal Basin. | 3c)Carry out assessments and issue reports; including recommendations on training to be addressed under project output 2.1.5 and identification of needs for strengthening biodiversity standards (developed through activity 1.1.7)
3d) Identify participants and the institutes and consultants to carry out training program
3e) Develop training materials (including translation) – for on site and distance learning
3g) Monitor results through questionnaires and web communications & revise program based on lessons learned
3h) Completion review and post-project continuation planning
2.4: The harmonized Baikal Basin Water Quality Monitoring program set under implementation, including upgraded monitoring stations. | 5a) Identify, assess and map water quality monitoring activity in the basin, including number, location technology and contaminants screened at all monitoring sites; analysis capabilities as well as monitoring protocols (include results from Selenga Delta study 1.1.2)
5b) Conduct inter-calibration exercise
5c)Develop early warning program to notify downstream users in the case of acute threats from water-borne pollutants.
5d)Conduct pollution warning / alert /response simulation(s)
5e)Develop recommendations and cost enhancements to existing monitoring regime
5f) Upgrade monitoring systems in both countries
5g) Follow up assessment during yr 4 of monitoring program progress.
Outcome 3: Mainstreaming ecosystem services.
3.1: Strategies implemented at 3 sites for mainstreaming biodiversity into mining. |  | 3a) ID priority demonstration sites.
3b) Carry-out on-site inspection of the selected mining facilities
3c) Elaborate voluntary and mandatory approaches to avoid or minimize pollution and sedimentation threats to aquatic ecosystem health.
3d) Negotiate agreement with mine management and government on protection effort and incentives.
3e) Implementation of recommendations by participating industries
3f) Monitor sites during project years 3 & 4.
3g) Publicize achievements and draft replication strategy
2a) Review incidences of anthrax outbreaks over last 20 years
3.2: Demonstration and strategy development for (dead) livestock disposal to cease periodic anthrax outbreaks |  | 2b) Carry out on-site inspections of rendering plants and waste disposal facilities
2c) Assess carcass handling practices leading to outbreaks and develop / cost out needed improvements in handling and disposal
2d) Review and provide recommendations concerning state veterinary inspections
2e) Seek country and international financial sources for implementing recommendations
2f) State agencies and industries to implement recommendations
2g) Monitor improvements and any subsequent outbreaks
3.3: Pilot for mainstreaming biodiversity and ecosystem health management objectives into tourism planning and practice. |  | 1a) Develop biodiversity compatible tourism plans.
1b) Pilot/model sport fishing program on low-impact sensitive sport fishing tourism in the Baikal Basin.
1c) Conduct peer to peer training using pilot area as training base.
3.4: Replication set: Lake Baikal Center to support dissemination of pollution-prevention and biodiversity conservation technologies; series of forums for industry interests on sustainable development priorities; support to NGOs rendered. |  | 5a) Develop communication and public awareness plan
5b) Launch web site (translated) and update
5c) Conduct surveys of tourists to determine pollution awareness and ecotourism interests
5d) Develop documentary concept and agree with Russian & international institutions (BBC, National Geographic, etc) on its development
5e) Establish the Baikal Industry Roundtable with private sector support, serving as a mechanism for exchanging views and also initiating public/private partnerships for water quality and biodiversity protection measures
5f)Establish the Baikal NGO Forum, providing a link to local NGOs.
5g) Develop a set of high profile activities, including shoreline cleanup campaigns for Lake Baikal, Lake Hövsgöl and the Selenga River, with NGO and Industry support, framed around an annual week of events during peak tourism season (July/August).

## Project budget
GEF Outcome / Atlas Activity |  | Responsible Party / Implementing Agent | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount Year 1 (USD) | Amount Year 2 (USD) | Amount Year 3 (USD) | Amount Year 4 (USD) | Total (USD)
Outcome 1: Strategic Policy and Planning Framework |  | MNRE | 62000 | GEF | 71200 | Int'l Consultants | 24,000 | 33,000 | 48,000 | 30,000 | 135,000 | 1
[5 empty] | 71300 | Local Consultants | 43,225 | 49,425 | 54,425 | 48,175 | 195,250 | 2
[5 empty] | 71600 | Travel | 14,500 | 14,500 | 0 | 0 | 29,000 | 3
[5 empty] | 72100 | Contractual Services | 215,000 | 197,000 | 6,000 | 0 | 418,000 | 4
[5 empty] | 72200 | Equipment | 21,400 | 0 | 0 | 0 | 21,400 | 5
[5 empty] | 74200 | Publications | 15,000 | 0 | 0 | 15,000 | 30,000 | 6
[5 empty] | 75700 | Misc-Training | 70,000 | 15,000 | 0 | 0 | 85,000 | 7
[5 empty] | 74500 | Misc - Services | 1,030 | 1,000 | 1,000 | 1,250 | 4,280 | 8
[5 empty] | Total Outcome 1: |  | 404,155 | 309,925 | 109,425 | 94,425 | 917,930
Outcome 2: Institutional Strengthening for IWRM. |  |  | 62000 | GEF | 71200 | Int'l Consultants | 46,000 | 36,000 | 14,000 | 0 | 96,000 | 9
[5 empty] | 71300 | Local Consultants | 45,000 | 48,500 | 39,500 | 39,500 | 172,500 | 10
[5 empty] | 71600 | Travel | 14,000 | 14,000 | 14,000 | 14,000 | 56,000 | 11
[5 empty] | 72100 | Contractual Services | 114,000 | 65,000 | 40,000 | 0 | 219,000 | 12
[5 empty] | 72200 | Equipment | 0 | 0 | 0 | 0 | 0 | 13
[5 empty] | 74200 | Publications | 25,000 | 40,000 | 45,000 | 0 | 110,000 | 14
[5 empty] | 75700 | Misc- Training | 0 | 30,000 | 30,000 | 30,000 | 90,000 | 15
[5 empty] | 74500 | Misc - Services | 2,320 | 2,000 | 2,000 | 1,714 | 8,034 | 16
[5 empty] | Total Outcome 2: |  | 246,320 | 235,500 | 184,500 | 85,214 | 751,534
Outcome 3: Mainstreaming ecosystem services |  |  | 62000 | GEF | 71200 | Int'l Consultants | 40,000 | 40,000 | 46,000 | 0 | 126,000 | 17
[5 empty] | 71300 | Local Consultants | 123,170 | 126,080 | 126,080 | 126,080 | 501,410 | 18
[5 empty] | 71600 | Travel | 53,000 | 53,000 | 53,000 | 53,000 | 212,000 | 19
[5 empty] | 72100 | Contractual Services | 0 | 130,000 | 230,000 | 35,000 | 395,000 | 20
[5 empty] | 72200 | Equipment | 50,000 | 19,000 | 0 | 0 | 69,000 | 21
[5 empty] | 74100 | Professional Services | 5,000 | 50,000 | 5,000 | 60,000 | 120,000 | 22
[5 empty] | 74200 | Publications | 0 | 20,000 | 30,000 | 10,000 | 60,000 | 23
[5 empty] | 75700 | Misc- Training | 52,000 | 50,000 | 130,000 | 115,000 | 347,000 | 24
[5 empty] | 74500 | Misc - Services | 3,000 | 3,000 | 3,000 | 4,764 | 13,764 | 25
[5 empty] | Total Outcome 3: |  | 326,170 | 491,080 | 623,080 | 403,844 | 1,844,174
Project Management Costs |  |  | 62000 | GEF | 71400 | Contractual Services - Individual | 80,210 | 80,210 | 80,210 | 80,210 | 320,840 | 26
[5 empty] | 71600 | Travel | 10,000 | 10,000 | 10,000 | 10,000 | 40,000 | 27
[5 empty] | 72200 | Equipment | 13,522 | 0 | 0 | 0 | 13,522 | 28
[5 empty] | 72400 | Communication | 1,000 | 1,000 | 1,000 | 1,000 | 4,000 | 29
[5 empty] | 72500 | Supplies | 1,000 | 1,000 | 0 | 0 | 2,000 | 30
[5 empty] | 74500 | Misc - Services | 1,000 | 1,000 | 1,000 | 1,000 | 4,000 | 31
[5 empty] | Total Management |  | 106,732 | 93,210 | 92,210 | 92,210 | 384,362
GRAND TOTALS |  |  | 62000 | GEF | 71200 | Int'l Consultants | 110,000 | 109,000 | 108,000 | 30,000 | 357,000
[5 empty] | 71300 | Local Consultants | 211,395 | 224,005 | 220,005 | 213,755 | 869,160
[5 empty] | 71400 | Contractual Services - Individual (Management) | 80,210 | 80,210 | 80,210 | 80,210 | 320,840
[5 empty] | 71600 | Travel | 91,500 | 91,500 | 77,000 | 77,000 | 337,000
[5 empty] | 72100 | Contractual Services | 329,000 | 392,000 | 276,000 | 35,000 | 1,032,000
[5 empty] | 72200 | Equipment | 84,922 | 19,000 | 0 | 0 | 103,922
[5 empty] | 72400 | Communications | 1,000 | 1,000 | 1,000 | 1,000 | 4,000
[5 empty] | 72500 | Supplies | 1,000 | 1,000 | 0 | 0 | 2,000
[5 empty] | 74100 | Professional Services | 5,000 | 50,000 | 5,000 | 60,000 | 120,000
[5 empty] | 74200 | Publications | 40,000 | 60,000 | 75,000 | 25,000 | 200,000
[5 empty] | 75700 | Misc -Training | 122,000 | 95,000 | 160,000 | 145,000 | 522,000
[5 empty] | 74500 | Misc - Services | 7,350 | 7,000 | 7,000 | 8,728 | 30,078
[5 empty] | Total Project |  | 1,083,377 | 1,129,715 | 1,009,215 | 675,693 | 3,898,000
Budget Note
1 | Causal chain TDA workshop leader expert (33k); Lead consultant on pollution hotspot analysis (24k); SAP development expert to lead SAP preparation exercise (48k); Sub-basin watershed management planning expert (30k);
2 | PM technical input to strategic policy and planning (15 weeks @ 750wk = 11,250). ABE - (80weeks @ 700/wk = 56,000); Science Advisory/Expert Working Group for TDA (5 members @ 16 weeks each = 80k); Working group to draft SAP elaborating biodiversity management objectives for key economic sectors of Baikal Basin (3 members @ 16 weeks each = 48000);
3 | Travel costs for four int'l experts, air fare, dsa. (29k).
4 | UNESCO subcontract to lead ground water assessment work under Output 3 and Khara River pollution assessment (250k); Selenga Delta Study (92k); Pollution hotspot assessment of the transboundary Baikal Basin (70k); EIA and tourism policy analysis for mainstreaming opportunities/constraints (6K).
5 | Field testing equipment for groundwater quality and sediment contamination.
6 | TDA published in Russian, English, Mongolian 15k; State of Baikal Basin Report (15k);
7 | Baikal Science Symposium (70k); Workshops for SAP development 15k.
8 | Miscellaneous
9 | Capacity Assessment and Training Programme Development Expert (20 weeks = 60k); Water law expert (12 weeks or 36k)
10 | PM technical input to pilot work to institutional strengthening (18 weeks 13.5k). ABE technical input to pilot work (70 weeks @ 700/wk = 49k); SAG support for Joint Commission, 5 people each @ 2 weeks each/year @ 1000/week (40k); 2 water law experts (Russia and Mongolia) -- 20K. 2 mining law experts (18k); Two capacity self assessment/training experts to work with int'l experts. 16 weeks each or 32 weeks -- 32,000.
11 | Joint Commission meetings at 10,000 each. Domestic travel associated with work under this component. Meeting costs/DSA for the Interagency Working Group on Selenga Basin - Mongolia--5 people 2x/year 2 days (16k) with PMU support;
12 | Output 2.3 Knowledge management/Training programme and module development (39k); harmonized Baikal Basin water quality monitoring programme (190,000)
13 | Zero budgeted.
14 | Output 3.3 Knowledge management/Training module development (90,000); Training modules printed and made available on the web (20k).
15 | Training events covering the costs of bringing people from around Russia to training venues for targeted training in key issues relevant to ecosystem conservation and mainstreaming biodiversity into productive sectors in Baikal.
16 | Meeting logistics costs associated with pilot activities, community working groups, Mapping and documentation for tourism management planning.
17 | Biodiversity Mainstreaming and Mining Expert (16 weeks 48k). Biodiversity mainstreaming and Tourism specialist (16 weeks 48k); Public participation strategy expert (10 weeks 30k).
18 | PM technical input 19 weeks (14.25k); ABE 58 weeks = 40.6k); Technical Communications and Partnership Building (208 weeks = 128,960); TCD-M -- (208 weeks = 145.6k); TA-M (208 weeks = 104k); Interactive SPA website design for web-based Baikal Center completed (20k). Mainstreaming biodiversity objectives into mining and tourism (2 experts 1k/week 12 weeks each or 24k); Veterinary and sanitation experts (2 experts 1000/week, 24 weeks total or 24k);
19 | Improving transbourndary cooperation 1 conference, 2 workshops, 3 support meetings for JC (80k); Study tours to pilot sites (60k); PTC travel to pilot regions (8k/year x 4 = 32k); Travel costs associated with monitoring/collecting monitoring data (40K).
20 | Aquatic biodiversity mainstreaming approaches for four case study situations within the mining sector of the Baikal Basin (130k); Aquatic biodiversity compatible tourism planning and training for Russian Baikal and for Mongolian Baikal (130k); Pilot biodiversity friendly sport fishing program 135k.
21 | Water quality monitoring buoys (50k); Practical simple field monitoring equipment for mainstreaming demonstrations.
22 | Audit (20k); Mid-Term and Terminal Evaluations (100k)
23 | Guidelines in Russian and Mongolian for mainstreaming biodiversity conservation objectives into mining, tourism and sport fishing practice (30k) Baikal information center online publications and content production and maintenance (80k)
24 | Inception workshop, SC (52k), field visits, Closing workshop (25k); Peer to peer training on mainstreaming in mining, tourism and sportfishing using pilot site areas (180,000); Baikal NGO forum (90,000);
25 | Miscellaneous
26 | Cost of management-related input of PMCU staff time (PM, PSMs, FA)
27 | Management-related travel to project sites
28 | Laptops for mobile management across 11 time zones and two countries
29 | Communications costs for staff while traveling – mobile cards, skype out calls, etc..
30 | Miscellaneous office supplies, batteries, etc.
31 | Office equipment repair, servicing, unforeseen service needs for any modern office.

## First year workplan
Outputs |  | Activities | Y1Q1 | Y1Q2 | Y1Q3 | Y1Q4 | Note
1.1: Transboundary Diagnostic Analysis of threats to the Baikal Basin ecosystem including Hövsgöl lake in Mongolia completed | 1.1 | 1a) Establish Science Advisory Group |  | 1 | 1 |  | one indicator (26K)
| 1.1 | 1b) Hold Science Symposium within 6 months of project inception |  |  | 1
| 1.1 | 1c) Hold stakeholder meetings. to include civil society. industry and local government representatives. to discuss ecosystem threats. |  |  | 1 | 1
| 1.1 | 1d) Revise and enhance preliminary TDA. including causal chain analysis |  |  |  | 1
1.2: Study on Selenga Delta habitat and water quality issues. including PTS and nutrient loading. water level fluxes and health of sediment and benthic organisms | 1.2 | 2a) Establish / upgrade monitoring sites at inflow. midpoint and outflow locations in the Delta. |  | 1 | 1 | 1
| 1.2 | 2b) Establish baselines relating to water balance and fluxes. water quality. the composition of benthic systems and sediment. diversity of aquatic flora and fauna (including presence of alien species). and presence/use of terrestrial species.(yr 1-2) |  |  | 1 | 1
1.3Assessment of transboundary problems in integrated surface and ground water resources management in the Baikal Basin and corresponding pollution threats. | 1.3 | 4a) Undertake groundwater assessment of the basin using available monitoring sites. |  |  |  | 1
| 1.3 | 4b) Provide monitoring results for the Basin Database, TDA and SOE reports.
1.4 Pollution hot spot assessment of the Basin. including a prioritized list of projects to be considered for future investment. the development of prefeasibility studies and revised regulations to reduce industrial pollution loading into the Baikal/Selenga basin. | 1.4 | 5a) Identify and map all significant industrial hot spots in the Basin. including both active and closed industrial facilities. Prioritize hot spot list based on significance of known risk to surface and groundwater. focusing on: a) waters used for drinking water abstraction. b) proximity to PA. Lake Baikal and Lake Hövsgöl. and spawning grounds c) specific hazardous pollutants used in processes or stored d) significant threat in case of natural disaster: e.g. earthquake or flood. |  | 1 | 1 | 1
| 1.4 | 5b) Review and rank upgrade needs for Selenga basin municipalities. including ID of ongoing and planned water and sanitation projects. |  |  |  | 1
1.6: Biodiversity conservation standards for tourism. mining. developed. integrated in SAP and local legislation. regional development plans; with amendments to EIA policies to address biodiversity risks; | 1.6 | 7a) Elaborate best practice conservation standards for tourism. mining using international and regional examples. |  |  | 1 | 1
| 1.6 | 7b) Provide gap analysis concerning best practices and the existing policies and standards in Russia and Mongolia. Develop recommendations for changes to local and national policies. legislation and regional development plans to enhance biodiversity protection.(Build on findings and recommendations from self-assessments developed in 2.1.3) |  |  |  | 1
1.7: Sub-basis watershed management plans development (for Mongolia) and implemented (for Russia). | 1.7 | 8ra) Assess current basin management strengths and weaknesses |  |  |  | 1
404155
2.1: Joint Commission for the Baikal / Selenga Basin established and capacitated on the basis of the current joint Russian - Mongolian Task Force on Transboundary Water Use and Protection. | 2.1 | 1a) Assist countries with selection. capacity building and information transfer to new Joint Commission participants |  | 1
| 2.1 | 1b) Facilitate Joint Commission inception meeting and annual meetings |  |  | 1
| 2.1 | 1c) Facilitate support of Science Advisory Group to the Joint Commission |  |  | 1
| 2.1 | 1d) Support Joint Commission review process for TDA and SAP approvals |  |  | 1
2.2:Inter-ministerial committees at national levels tasked with managing the decision-making process to approve and implement Baikal basin initiatives. incl. integrated sub-basin watershed management plans. TDA/SAP. | 2.2 | 2a) Designation by countries of participants and holding of interministerial meetings |  |  |  | 1
| 2.2 | 2b) At country request. participate in interministerial meetings to clarify purpose. benefits and impacts of proposals. including TDA/SAP. transboundary waters treaty. etc. |  |  |  | 1
| 2.3 | 3a) Develop guidance for self-assessments |  |  | 1 | 1
2.3:Training program carried out for key actors in an improved and enhanced. long-term transboundary management of Baikal Basin. | 2.3 | 3b) Hold training workshops for persons carrying out self-assessments |  |  |  | 1
| 2.3 | 3d) Identify participants and the institutes and consultants to carry out training program |  |  |  | 1
| 2.4 | 5a) Identify. assess and map water quality monitoring activity in the basin. including number. location technology and contaminants screened at all monitoring sites; analysis capabilities as well as monitoring protocols (include results from Selenga Delta study 1.1.2) |  |  | 1 | 1
246320
3.3: Pilot for mainstreaming biodiversity and ecosystem health management objectives into tourism planning and practice. | 3.3 | 1a) Develop biodiversity compatible tourism plans. |  |  |  | 1
| 3.4 | 5a) Develop communication and public awareness plan |  | 1
3.4: Replication set: Lake Baikal Center to support dissemination of pollution-prevention and biodiversity conservation technologies; series of forums for industry interests on sustainable development priorities; support to NGOs rendered. | 3.4 | 5b) Launch web site (translated) and update |  |  | 1
| 3.4 | 5c) Conduct surveys of tourists to determine pollution awareness and ecotourism interests |  | 1
326170

## First year budget
GEF Outcome / Atlas Activity | Responsible Party / Implementing Agent | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount Year 1 (USD)
Outcome 1: Strategic Policy and Planning Framework | MNRE | 62000 | GEF | 71200 | Int'l Consultants | 24,000
|  |  |  | 71300 | Local Consultants | 43,225
|  |  |  | 71600 | Travel | 14,500
|  |  |  | 72100 | Contractual Services | 215,000
|  |  |  | 72200 | Equipment | 21,400
|  |  |  | 74200 | Publications | 15,000
|  |  |  | 75700 | Misc-Training | 70,000
|  |  |  | 74500 | Misc - Services | 1,030
|  |  |  | Total Outcome 1: |  | 404,155
Outcome 2: Institutional Strengthening for IWRM. |  | 62000 | GEF | 71200 | Int'l Consultants | 46,000
|  |  |  | 71300 | Local Consultants | 45,000
|  |  |  | 71600 | Travel | 14,000
|  |  |  | 72100 | Contractual Services | 114,000
|  |  |  | 72200 | Equipment | 0
|  |  |  | 74200 | Publications | 25,000
|  |  |  | 75700 | Misc- Training | 0
|  |  |  | 74500 | Misc - Services | 2,320
|  |  |  | Total Outcome 2: |  | 246,320
Outcome 3: Mainstreaming ecosystem services |  | 62000 | GEF | 71200 | Int'l Consultants | 40,000
|  |  |  | 71300 | Local Consultants | 123,170
|  |  |  | 71600 | Travel | 53,000
|  |  |  | 72100 | Contractual Services | 0
|  |  |  | 72200 | Equipment | 50,000
|  |  |  | 74100 | Professional Services | 5,000
|  |  |  | 74200 | Publications | 0
|  |  |  | 75700 | Misc- Training | 52,000
|  |  |  | 74500 | Misc - Services | 3,000
|  |  |  | Total Outcome 3: |  | 326,170
Project Management Costs |  | 62000 | GEF | 71400 | Contractual Services - Individual | 80,210
|  |  |  | 71600 | Travel | 10,000
|  |  |  | 72200 | Equipment | 13,522
|  |  |  | 72400 | Communication | 1,000
|  |  |  | 72500 | Supplies | 1,000
|  |  |  | 74500 | Misc - Services | 1,000
|  |  |  | Total Management |  | 106,732
GRAND TOTALS |  | 62000 | GEF | 71200 | Int'l Consultants | 110,000
|  |  |  | 71300 | Local Consultants | 211,395
|  |  |  | 71400 | Contractual Services - Individual (Management) | 80,210
|  |  |  | 71600 | Travel | 91,500
|  |  |  | 72100 | Contractual Services | 329,000
|  |  |  | 72200 | Equipment | 84,922
|  |  |  | 72400 | Communications | 1,000
|  |  |  | 72500 | Supplies | 1,000
|  |  |  | 74100 | Professional Services | 5,000
|  |  |  | 74200 | Publications | 40,000
|  |  |  | 75700 | Misc -Training | 122,000
|  |  |  | 74500 | Misc - Services | 7,350
|  |  |  | Total Project |  | 1,083,377