## Project workplan
Outputs | Activities |  | Yr 1 |  |  |  | Yr 2 |  |  |  |  | Yr 3 |  |  |  |  | Yr 4
|  |  | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 | Cofinansing
Outcome 1. Strategic Policy & Planning
1.1: Transboundary Diagnostic Analysis of threats to the Baikal Basin ecosystem including Hövsgöl lake in Mongolia completed | 1a) Establish Science Advisory Group
| 1b) Hold Science Symposium within 6 months of project inception | [20 empty] | Росгидромет
| 1c) Hold stakeholder meetings, to include civil society, industry and local government representatives, to discuss ecosystem threats. | [20 empty] | БИП
| 1d) Revise and enhance preliminary TDA, including causal chain analysis | [20 empty] | Роспотребнадзор
1e) Update TDA as a Baikal Basin State of the Environment Report no later than 6 months prior to the end of the project, including evidence of status changes since the initial TDA.
1.2: Study on Selenga Delta habitat and water quality issues, including PTS and nutrient loading, water level fluxes and health of sediment and benthic organisms | 2a) Establish / upgrade monitoring sites at inflow, midpoint and outflow locations in the Delta. | [20 empty] | Росгидромет
| 2b) Establish baselines relating to water balance and fluxes, water quality, the composition of benthic systems and sediment, diversity of aquatic flora and fauna (including presence of alien species), and presence/use of terrestrial species.(yr 1-2) | [20 empty] | Росрыболовство
| 2c) Develop and present analysis on the impact to delta flora and fauna of changing water conditions, including recommendations on optimal flows; as well as in-stream constructed wetlands and other design options to reduce the flow of pollutants into and through the delta (yr 2) | [20 empty] | БИП
| 2d) Monitor water quality and flora/fauna conditions at monitoring sites on permanent basis | [20 empty] | Роспотребнадзор
1.3Assessment of transboundary problems in integrated surface and ground water resources management in the Baikal Basin and corresponding pollution threats. | 3a) Undertake groundwater assessment of the basin using available monitoring sites. | [20 empty] | БИП
3b) Provide monitoring results for the Basin Database, TDA and SOE reports.
3c) Link with training / capacity building activities (see output 2.1.4) to improve environmental inspections and enforcement of regulations for avoiding groundwater contamination.
3d) Develop and cost out recommended national groundwater management policies for each country, including inter-sectoral integration and planning, well head protection, expanded groundwater monitoring (see output 2.1.5)
1.4 Pollution hot spot assessment of the Basin, including a prioritized list of projects to be considered for future investment, the development of prefeasibility studies and revised regulations to reduce industrial pollution loading into the Baikal/Selenga basin. | 4a) Identify and map all significant industrial hot spots in the Basin, including both active and closed industrial facilities. Prioritize hot spot list based on significance of known risk to surface and groundwater, focusing on: a) waters used for drinking water abstraction, b) proximity to PA, Lake Baikal and Lake Hövsgöl, and spawning grounds c) specific hazardous pollutants used in processes or stored d) significant threat in case of natural disaster: e.g. earthquake or flood. | [20 empty] | Байкалводресурсы
| 4b) Review and rank upgrade needs for Selenga basin municipalities, including ID of ongoing and planned water and sanitation projects. | [20 empty] | Fund for Protection of Lake Baikal
| 4c) Provide assistance to high risk / high priority hot spots for a) development of pre-feasibility studies for remediation on closed facilities, b) training for active concerns on PTS, POPs & UPOPs, management, c) recommendations on environmental investments on active concerns to reduce pollution discharge. | [20 empty] | БИП
| 4d)Develop recommendations on revised regulations and inspection policies for large industrial facilities in the region | [20 empty] | Роспотребнадзор
1.5. Strategic Action Programme (SAP) under implementation, including joint actions to enhance ecosystem protection | 5a) Form SAP group to develop and submit SAP | [20 empty] | Ministry of Natural Resources of the Republic of Buryatia | МПР
| 5a1) Develop draft structure SAP | [20 empty] | Байкалводресурсы
| 5b) Submit SAP draft to both governments for approval at Ministers meeting (Yr 3) | [20 empty] | БИП
5c) Provide advise and assistance to both countries on SAP implementation (yr 4)
5d) Monitor country achievement of SAP implementation
1.6: Biodiversity conservation standards for tourism, mining, fisheries and livestock management developed, integrated in SAP and local legislation, regional development plans; with amendments to EIA policies to address biodiversity risks; | 6a) Elaborate best practice conservation standards for tourism, mining using international and regional examples. | [20 empty] | БГУ
| 6b) Provide gap analysis concerning best practices and the existing policies and standards in Russia and Mongolia. Develop recommendations for changes to local and national policies, legislation and regional development plans to enhance biodiversity protection.(Build on findings and recommendations from self-assessments developed in 2.1.3) | [20 empty] | БИП | консультанты
| 6c) Propose ecotourism and pollution avoidance aspects for tourism plans in the region, especially those being developed in Irkutsk and Buryatia. | [20 empty] | Роспотребнадзор
1.7: Sub-basis watershed management plans development (for Mongolia) and implemented (for Russia). | 7ma) hold kick off meeting with local officials in each basin
| 7mb) collect data on economic activities, such as transportation, industry, agriculture and tourism and their impacts on the environment: (e.g. water quality, biodiversity), | [20 empty] | Ministry of Natural Resources of the Republic of Buryatia | МПР
| 7mc)draft sub-basin management plan(s) | [20 empty] | Росрыболовство
| 7md) present plan(s) to key stakeholders in series of workshops | [20 empty] | БИП
| 7me) revise and submit plans for government approvals | [21 empty] | водосбор Тугнуй-Сухара/Бурятия - консультант 3500
| 7mf) establish training and capacity building as necessary for newly responsible agencies | [21 empty] | водосбор Голустяная/Иркутск - 3500
| 7mg) assist Mongolian government on policy and legal changes requires | [21 empty] | водосбор Хилок/Забайкальский край - 3500
In Mongolia:
7mh) Hold workshops with agencies focusing on industrial development and tourism to forge cooperation
In Russia:
7ra) Assess current basin management strengths and weaknesses
7rb)Launch capacity building and training program (also see output 2.1.4.)for sub basin managers, on integrated planning, mapping using GIS, and biodiversity monitoring
7rc) Hold workshops with agencies focusing on industrial development, transportation and tourism to forge closer cooperation.
Outcome 2: Institutional strengthening for Integrated Water Resource Management (IWRM)
2.1: Joint Commission for the Baikal / Selenga Basin established and capacitated on the basis of the current joint Russian - Mongolian Task Force on Transboundary Water Use and Protection. | 1a) Assist countries with selection, capacity building and information transfer to new Joint Commission participants | [20 empty] | Росгидромет
1b) Facilitate Joint Commission inception meeting and annual meetings
1c) Facilitate support of Science Advisory Group to the Joint Commission
1d) Support Joint Commission review process for TDA and SAP approvals
1e) Support Joint Commission efforts to draft new Treaty
2.2:Inter-ministerial committees at national levels tasked with managing the decision-making process to approve and implement Baikal basin initiatives, incl. integrated sub-basin watershed management plans, TDA/SAP. | 2a) Designation by countries of participants and holding of interministerial meetings | [20 empty] | Байкалводресурсы
| 2b) At country request, participate in interministerial meetings to clarify purpose, benefits and impacts of proposals, including TDA/SAP, transboundary waters treaty, etc. | [20 empty] | БИП
| 3a) Develop guidance for self-assessments | [20 empty] | БГУ
| 3b) Hold training workshops for persons carrying out self-assessments | [20 empty] | БИП
2.3:Training program carried out for key actors in an improved and enhanced, long-term transboundary management of Baikal Basin. | 3c)Carry out assessments and issue reports; including recommendations on training to be addressed under project output 2.1.5 and identification of needs for strengthening biodiversity standards (developed through activity 1.1.7)
3d) Identify participants and the institutes and consultants to carry out training program
3e) Develop training materials (including translation) – for on site and distance learning
3g) Monitor results through questionnaires and web communications & revise program based on lessons learned
3h) Completion review and post-project continuation planning
2.4: The harmonized Baikal Basin Water Quality Monitoring program set under implementation, including upgraded monitoring stations. | 4a) Identify, assess and map water quality monitoring activity in the basin, including number, location technology and contaminants screened at all monitoring sites; analysis capabilities as well as monitoring protocols (include results from Selenga Delta study 1.1.2) | [20 empty] | Ministry of Natural Resources of the Republic of Buryatia | МПР
| 4b) Conduct inter-calibration exercise | [20 empty] | Росгидромет
| 4c)Develop early warning program to notify downstream users in the case of acute threats from water-borne pollutants. | [20 empty] | БИП
| 4d)Conduct pollution warning / alert /response simulation(s) | [20 empty] | Роспотребнадзор
4e)Develop recommendations and cost enhancements to existing monitoring regime
4f) Upgrade monitoring systems in both countries
4g) Follow up assessment during yr 4 of monitoring program progress.
Outcome 3: Mainstreaming ecosystem services.
3.1: Strategies implemented at 3 sites for mainstreaming biodiversity into mining. |  | 1a) ID priority demonstration sites. | [19 empty] | Ministry of Natural Resources of the Republic of Buryatia | МПР
|  | 1b) Carry-out on-site inspection of the selected mining facilities | [19 empty] | Fund for Protection of Lake Baikal
|  | 1c) Elaborate voluntary and mandatory approaches to avoid or minimize pollution and sedimentation threats to aquatic ecosystem health. | [19 empty] | БИП
1d) Negotiate agreement with mine management and government on protection effort and incentives.
1e) Implementation of recommendations by participating industries
1f) Monitor sites during project years 3 & 4.
1g) Publicize achievements and draft replication strategy
3.2: Demonstration and strategy development for (dead) livestock disposal to cease periodic anthrax outbreaks |  | 2a) Review incidences of anthrax outbreaks over last 20 years | [19 empty] | Ministry of Natural Resources of the Republic of Buryatia | МПР
|  | 2b) Carry out on-site inspections of rendering plants and waste disposal facilities | [19 empty] | Veterinary Authority Of The Republic Of Buryatia
2c) Assess carcass handling practices leading to outbreaks and develop / cost out needed improvements in handling and disposal
2d) Review and provide recommendations concerning state veterinary inspections
2e) Seek country and international financial sources for implementing recommendations
2f) State agencies and industries to implement recommendations
2g) Monitor improvements and any subsequent outbreaks
3.3: Pilot for mainstreaming biodiversity and ecosystem health management objectives into tourism planning and practice. |  | 3a) Develop biodiversity compatible tourism plans. | [19 empty] | Росгидромет
|  | 3b) Pilot/model sport fishing program on low-impact sensitive sport fishing tourism in the Baikal Basin. | [19 empty] | БГУ
3c) Conduct peer to peer training using pilot area as training base.
3.4: Replication set: Lake Baikal Center to support dissemination of pollution-prevention and biodiversity conservation technologies; series of forums for industry interests on sustainable development priorities; support to NGOs rendered. |  | 4a) Develop communication and public awareness plan | [19 empty] | Ministry of Natural Resources of the Republic of Buryatia | МПР
|  | 4b) Launch web site (translated) and update | [19 empty] | Fund for Protection of Lake Baikal
4c) Conduct surveys of tourists to determine pollution awareness and ecotourism interests
4d) Develop documentary concept and agree with Russian & international institutions (BBC, National Geographic, etc) on its development
4e) Establish the Baikal Industry Roundtable with private sector support, serving as a mechanism for exchanging views and also initiating public/private partnerships for water quality and biodiversity protection measures
4f)Establish the Baikal NGO Forum, providing a link to local NGOs.
4g) Develop a set of high profile activities, including shoreline cleanup campaigns for Lake Baikal, Lake Hövsgöl and the Selenga River, with NGO and Industry support
4h) Framed around an annual week of events during peak tourism season (July/August).

## Second year workplan
Outputs | Activities | Responsibility | Expected completion | 2013 |  |  |  | Yr 3
|  |  |  | Q1 | Q2 | Q3 | Q4
Outcome 1. Strategic Policy & Planning
1.1: Transboundary Diagnostic Analysis of threats to the Baikal Basin ecosystem including Hövsgöl lake in Mongolia completed | 1d) Revise and enhance preliminary TDA, including causal chain analysis
2d) Monitor water quality and flora/fauna conditions at monitoring sites on permanent basis
1.3Assessment of transboundary problems in integrated surface and ground water resources management in the Baikal Basin and corresponding pollution threats. | 3a) Undertake groundwater assessment of the basin using available monitoring sites.
3b) Provide monitoring results for the Basin Database, TDA and SOE reports.
3c) Link with training / capacity building activities (see output 2.1.4) to improve environmental inspections and enforcement of regulations for avoiding groundwater contamination.
3d) Develop and cost out recommended national groundwater management policies for each country, including inter-sectoral integration and planning, well head protection, expanded groundwater monitoring (see output 2.1.5)
1.4 Pollution hot spot assessment of the Basin, including a prioritized list of projects to be considered for future investment, the development of prefeasibility studies and revised regulations to reduce industrial pollution loading into the Baikal/Selenga basin. | 4c) Provide assistance to high risk / high priority hot spots for a) development of pre-feasibility studies for remediation on closed facilities, b) training for active concerns on PTS, POPs & UPOPs, management, c) recommendations on environmental investments on active concerns to reduce pollution discharge.
1.5. Strategic Action Programme (SAP) under implementation, including joint actions to enhance ecosystem protection | 5a) Form SAP group to develop and submit SAP
5a1) Develop draft structure SAP
1.6: Biodiversity conservation standards for tourism, mining developed, integrated in SAP and local legislation, regional development plans; with amendments to EIA policies to address biodiversity risks; | 6b) Provide gap analysis concerning best practices and the existing policies and standards in Russia and Mongolia. Develop recommendations for changes to local and national policies, legislation and regional development plans to enhance biodiversity protection.(Build on findings and recommendations from self-assessments developed in 2.1.3)
6c) Propose ecotourism and pollution avoidance aspects for tourism plans in the region, especially those being developed in Irkutsk and Buryatia.
1.7: Sub-basis watershed management plans development (for Mongolia) and implemented (for Russia). | 7ma) hold kick off meeting with local officials in each basin
7mb) collect data on economic activities, such as transportation, industry, agriculture and tourism and their impacts on the environment: (e.g. water quality, biodiversity),
7mc)draft sub-basin management plan(s)
7md) present plan(s) to key stakeholders in series of workshops
7me) revise and submit plans for government approvals
In Mongolia:
In Russia:
7ra) Assess current basin management strengths and weaknesses
7rb)Launch capacity building and training program (also see output 2.1.4.)for sub basin managers, on integrated planning, mapping using GIS, and biodiversity monitoring
7rc) Hold workshops with agencies focusing on industrial development, transportation and tourism to forge closer cooperation.
Outcome 2: Institutional strengthening for Integrated Water Resource Management (IWRM)
2.1: Joint Commission for the Baikal / Selenga Basin established and capacitated on the basis of the current joint Russian - Mongolian Task Force on Transboundary Water Use and Protection. | 1b) Facilitate Joint Commission inception meeting and annual meetings
1c) Facilitate support of Science Advisory Group to the Joint Commission
1d) Support Joint Commission review process for TDA and SAP approvals
1e) Support Joint Commission efforts to draft new Treaty
2.2:Inter-ministerial committees at national levels tasked with managing the decision-making process to approve and implement Baikal basin initiatives, incl. integrated sub-basin watershed management plans, TDA/SAP. | 2a) Designation by countries of participants and holding of interministerial meetings
2b) At country request, participate in interministerial meetings to clarify purpose, benefits and impacts of proposals, including TDA/SAP, transboundary waters treaty, etc.
2.3:Training program carried out for key actors in an improved and enhanced, long-term transboundary management of Baikal Basin. | 3c)Carry out assessments and issue reports; including recommendations on training to be addressed under project output 2.1.5 and identification of needs for strengthening biodiversity standards (developed through activity 1.1.7)
3e) Develop training materials (including translation) – for on site and distance learning
2.4: The harmonized Baikal Basin Water Quality Monitoring program set under implementation, including upgraded monitoring stations. | 4b) Conduct inter-calibration exercise
4c)Develop early warning program to notify downstream users in the case of acute threats from water-borne pollutants.
4d)Conduct pollution warning / alert /response simulation(s)
4e)Develop recommendations and cost enhancements to existing monitoring regime
Outcome 3: Mainstreaming ecosystem services.
3.1: Strategies implemented at 3 sites for mainstreaming biodiversity into mining. | 1a) ID priority demonstration sites.
1b) Carry-out on-site inspection of the selected mining facilities
1c) Elaborate voluntary and mandatory approaches to avoid or minimize pollution and sedimentation threats to aquatic ecosystem health.
1d) Negotiate agreement with mine management and government on protection effort and incentives.
3.2: Demonstration and strategy development for (dead) livestock disposal to cease periodic anthrax outbreaks | 2d) Review and provide recommendations concerning state veterinary inspections
2e) Seek country and international financial sources for implementing recommendations
2f) State agencies and industries to implement recommendations
3.3: Pilot for mainstreaming biodiversity and ecosystem health management objectives into tourism planning and practice. | 3a) Develop biodiversity compatible tourism plans.
3b) Pilot/model sport fishing program on low-impact sensitive sport fishing tourism in the Baikal Basin.
3.4: Replication set: Lake Baikal Center to support dissemination of pollution-prevention and biodiversity conservation technologies; series of forums for industry interests on sustainable development priorities; support to NGOs rendered. | 4b) Launch BIC web site (translated) and update | [6 empty] | Fund for Protection of Lake Baikal
4ba) Ecological atlas
4c) Conduct surveys of tourists to determine pollution awareness and ecotourism interests, Mongolia
4d) Develop documentary concept and agree with Russian & international institutions (BBC, National Geographic, etc) on its development
4e) Establish the Baikal Industry Roundtable with private sector support, serving as a mechanism for exchanging views and also initiating public/private partnerships for water quality and biodiversity protection measures
4f)Establish the Baikal NGO Forum, providing a link to local NGOs.
4h) Framed around an annual week of events during peak tourism season (July/August).