## 2012 workplan
Outputs | Activities |  | Responsibility | Expected completion | Yr 1 |  |  |  | Yr 2
[5 empty] | Q1 | Q2 | Q3 | Q4
Outcome 1. Strategic Policy & Planning
1.1: Transboundary Diagnostic Analysis of threats to the Baikal Basin ecosystem including Hövsgöl lake in Mongolia completed | 1a) Establish Science Advisory Group |  | Project Manager, Technical Directors | end of May 2012
| 1c) Hold stakeholder meetings, to include civil society, industry and local government representatives, to discuss ecosystem threats. |  |  | middle of August 2012
| 1d) Revise and enhance preliminary TDA, including causal chain analysis |  |  | middle of December 2012
1.2: Study on Selenga Delta habitat and water quality issues, including PTS and nutrient loading, water level fluxes and health of sediment and benthic organisms | 2a) Establish / upgrade monitoring sites at inflow, midpoint and outflow locations in the Delta. |  | Project Manager, Technical Directors | middle of December 2012
| 2b) Establish baselines relating to water balance and fluxes, water quality, the composition of benthic systems and sediment, diversity of aquatic flora and fauna (including presence of alien species), and presence/use of terrestrial species.(yr 1-2) |  | Project Manager, Technical Directors | middle of December 2012
| 2c) Develop and present analysis on the impact to delta flora and fauna of changing water conditions, including recommendations on optimal flows; as well as in-stream constructed wetlands and other design options to reduce the flow of pollutants into and through the delta (yr 2) |  | Project Manager, Technical Directors | middle of December 2012
| 2d) Monitor water quality and flora/fauna conditions at monitoring sites on permanent basis |  | Project Manager, Technical Directors | middle of December 2012
1.3Assessment of transboundary problems in integrated surface and ground water resources management in the Baikal Basin and corresponding pollution threats. | 3a) Undertake groundwater assessment of the basin using available monitoring sites. |  | Project Manager, UNESCO | end of February 2013
1.4 Pollution hot spot assessment of the Basin, including a prioritized list of projects to be considered for future investment, the development of prefeasibility studies and revised regulations to reduce industrial pollution loading into the Baikal/Selenga basin. | 4a) Identify and map all significant industrial hot spots in the Basin, including both active and closed industrial facilities. Prioritize hot spot list based on significance of known risk to surface and groundwater, focusing on: a) waters used for drinking water abstraction, b) proximity to PA, Lake Baikal and Lake Hövsgöl, and spawning grounds c) specific hazardous pollutants used in processes or stored d) significant threat in case of natural disaster: e.g. earthquake or flood. |  | Project Manager, Technical Directors, UNESCO | middle of November 2012
| 4b) Review and rank upgrade needs for Selenga basin municipalities, including ID of ongoing and planned water and sanitation projects. |  | Project Manager, Technical Directors, UNESCO | middle of November 2012
1.6: Biodiversity conservation standards for tourism, mining, integrated in SAP and local legislation, regional development plans; with amendments to EIA policies to address biodiversity risks; | 6a) Elaborate best practice conservation standards for tourism, mining using international and regional examples. |  | Project Manager, Technical Directors, Aquatic Bioresources Expert
| 6b) Provide gap analysis concerning best practices and the existing policies and standards in Russia and Mongolia. Develop recommendations for changes to local and national policies, legislation and regional development plans to enhance biodiversity protection.(Build on findings and recommendations from self-assessments developed in 2.1.3) |  | Project Manager, Technical Directors, Aquatic Bioresources Expert
1.7: Sub-basis watershed management plans development (for Mongolia) and implemented (for Russia). | 7ma) hold kick off meeting with local officials in each basin |  | Project Manager, Technical Directors | middle of June 2012
| 7mb) collect data on economic activities, such as transportation, industry, agriculture and tourism and their impacts on the environment: (e.g. water quality, biodiversity), |  | Project Manager, Technical Directors | middle of December 2012
| 7mc)draft sub-basin management plan(s) |  | Project Manager, Technical Directors | middle of December 2013
| 7mg) assist Mongolian government on policy and legal changes requires |  | Project Manager, Technical Directors | middle of December 2013
| In Mongolia: |  | Project Manager, Technical Directors | middle of December 2013
| 7mh) Hold workshops with agencies focusing on industrial development and tourism to forge cooperation |  | Project Manager, Technical Directors | end of September 2012
In Russia:
| 7ra) Assess current basin management strengths and weaknesses |  | Project Manager, Technical Directors | end of September 2012
| 7rb)Launch capacity building and training program (also see output 2.1.4.)for sub basin managers, on integrated planning, mapping using GIS, and biodiversity monitoring |  | Project Manager, Technical Directors | middle of December 2013
Outcome 2: Institutional strengthening for Integrated Water Resource Management (IWRM)
2.1: Joint Commission for the Baikal / Selenga Basin established and capacitated on the basis of the current joint Russian - Mongolian Task Force on Transboundary Water Use and Protection. | 1a) Assist countries with selection, capacity building and information transfer to new Joint Commission participants |  | Project Manager, Technical Directors | end of September 2012
| 1b) Facilitate Joint Commission inception meeting and annual meetings |  | Project Manager, Technical Directors, Project Administration and Logistics Officer | middle of October 2012
| 1c) Facilitate support of Science Advisory Group to the Joint Commission |  | Project Manager, Technical Directors, Project Administration and Logistics Officer | middle of December 2012
2.2:Inter-ministerial committees at national levels tasked with managing the decision-making process to approve and implement Baikal basin initiatives, incl. integrated sub-basin watershed management plans, TDA/SAP. | 2a) Designation by countries of participants and holding of interministerial meetings |  | Project Manager, Technical Directors, Project Administration and Logistics Officer | middle of December 2012
| 2b) At country request, participate in interministerial meetings to clarify purpose, benefits and impacts of proposals, including TDA/SAP, transboundary waters treaty, etc. |  | Project Manager, Technical Directors, Project Administration and Logistics Officer | middle of December 2012
2.3:Training program carried out for key actors in an improved and enhanced, long-term transboundary management of Baikal Basin. | 3a) Develop guidance for self-assessments |  | Project Manager, Technical Directors | end of September 2012
| 3b) Hold training workshops for persons carrying out self-assessments |  | Project Manager, Technical Directors, Project Administration and Logistics Officer | end of November 2012
| 3d) Identify participants and the institutes and consultants to carry out training program |  | Project Manager, Technical Directors | end of September 2012
2.4: The harmonized Baikal Basin Water Quality Monitoring program set under implementation, including upgraded monitoring stations. | 4a) Identify, assess and map water quality monitoring activity in the basin, including number, location technology and contaminants screened at all monitoring sites; analysis capabilities as well as monitoring protocols (include results from Selenga Delta study 1.1.2) |  | Project Manager, Technical Directors, Aquatic Bioresources Expert | middle of December 2012
| 4d)Conduct pollution warning / alert /response simulation(s) |  | Project Manager, Technical Directors | middle of December 2012
Outcome 3: Mainstreaming ecosystem services.
3.2: Demonstration and strategy development for (dead) livestock disposal to cease periodic anthrax outbreaks |  | 2a) Review incidences of anthrax outbreaks over last 20 years | Project Manager, Technical Directors, Aquatic Bioresources Expert | end of July 2012
|  | 2b) Carry out on-site inspections of rendering plants and waste disposal facilities | Project Manager, Technical Directors, Aquatic Bioresources Expert | middle of December 2013
|  | 2c) Assess carcass handling practices leading to outbreaks and develop / cost out needed improvements in handling and disposal | Project Manager, Technical Directors, Aquatic Bioresources Expert | middle of December 2012
|  | 2d) Review and provide recommendations concerning state veterinary inspections | Project Manager, Technical Directors, Aquatic Bioresources Expert | middle of December 2012
|  | 2e) Seek country and international financial sources for implementing recommendations | Project Manager, Technical Directors, Aquatic Bioresources Expert | middle of December 2015
3.3: Pilot for mainstreaming biodiversity and ecosystem health management objectives into tourism planning and practice. |  | 3a) Develop biodiversity compatible tourism plans. | Project Manager, Technical Directors, Aquatic Bioresources Expert | middle of December 2012
3.4: Replication set: Lake Baikal Center to support dissemination of pollution-prevention and biodiversity conservation technologies; series of forums for industry interests on sustainable development priorities; support to NGOs rendered. |  | 4a) Develop communication and public awareness plan | Project Manager, Technical Directors | middle of December 2012
|  | 4b) Launch web site (translated) and update | Project Manager, Technical Directors | middle of December 2012
|  | 4c) Conduct surveys of tourists to determine pollution awareness and ecotourism interests | Project Manager, Technical Directors | end of October 2012
|  | 4d) Develop documentary concept and agree with Russian & international institutions (BBC, National Geographic, etc) on its development | Project Manager, Technical Directors | middle of December 2012
|  | 4e) Establish the Baikal Industry Roundtable with private sector support, serving as a mechanism for exchanging views and also initiating public/private partnerships for water quality and biodiversity protection measures | Project Manager, Technical Directors | end of September 2012
|  | 4f)Establish the Baikal NGO Forum, providing a link to local NGOs. | Project Manager, Technical Directors | end of October 2012
|  | 4g) Develop a set of high profile activities, including shoreline cleanup campaigns for Lake Baikal, Lake Hövsgöl and the Selenga River, with NGO and Industry support | Project Manager, Technical Directors | middle of December 2015